## Summary
Metric | Source | Purpose | Data | Data Timeliness | Exceptions to Look For | Technique to extract this information | Available Already | Comments
Infill List | Infill List Spreadsheet | This list provides the basis for the rollout and all installations should ultimately be reconciled against this list. It will provide information about when regions have been completed (which is a trigger for optimisation) | - Meter ID - Region | Batch Check | - Unexpected installation (Not on infill list) | Pre-loaded List | Yes | This list includes the original 268,212 meters plus and additional ~1700 that are part of multi meter sites.
Exchange Service Order Creation | CIS (via ADW) | This indicates that an exchange about to commence for a site. This will allow us to measure open vs closed to look for trends that require attention. This also provides the comms card that will be replaced | - Service Order Number - NMI - Meter (asset) - Old Comms Card | Synchronised Daily | - Unexpected pending installation (Not on infill list) | Query in ADW | Yes
Installation Performed | FMC | Using FMC, the field status of the service order can be determined. This can also highlight exceptions that have occurred during the installation that explains why a site was missed | - Service Order Information - Job Status - Meter - Checklist Results (antennae, meter exchanged etc) - Skip Codes | Batch Request subject to installers synching field devices | - Skip Code Summary - Unexpected antenna installation | web service call to FMC | Partial
Exchange Service Order Closeout | CIS (via ADW) | This is used to indicate that a service order is complete. It should provide a status and also a reason if it has failed to complete. This will also provide an ageing indication of the install order. | - Closeout Status - BPEM Exceptions?? - Date of closeout | Synchronised Daily | - Aged service orders (open for > x weeks) - BPEM Exception Counts | Query in ADW | Partial | How to source exceptions from CIS? Is this data already in ADW?
CIS Standing Data Reconciled | CIS (via ADW) | To close the loop on a site from CIS perspective, this will confirm that what was intended from an FMC perspective was updated appropriately in CIS | - NMI - Meter (asset) - Comms Card | Real-time Sync | - FMC and CIS Align post service order closure - Comms Card in CIS is not a Mesh NIC | Query in ADW | Partial
Meter Loaded in UIQ | UIQ | All current AMI Meter stock is loaded into UIQ. This will detect installations on meters that are unknown. | - Meter ID | One-time Load | - Missing Meter Data Ship file from L&G | Pre-loaded List. Updated with new deliveries of meters | Yes
Meter Field Paired | UIQ | This provides an indication that a card has bound for meter where the exchange took place. This will also identify installations of meters that are not on the infill list. Should provide an aging indicator from exchange to comm. | - Meter Status - Joined MAC ID | Batch Request | - This will highlight non communicating meters - This will highlight password mismatches | Web Service call to UIQ | Yes
Meter Paired to Expected Comms Card | UIQ | This validates that the meter to comms card relationship in CIS is consistent with the actual card that is bound in UIQ | Data Check | Batch Check | - Meter Comms Card Mismatches | Web Service call to UIQ | Yes
Meter Location Loaded in UIQ | UIQ | This will validate the interim and M2M standing data update process. It will also potentially identify devices that are classified as Logically Converted in PN. | - NMI - Meter ID | Managed through Synch Process | - Standing Data Mismatch in UIQ | Web Service call to UIQ | Yes
Meter Location aligns to CIS | UIQ | This will validate the interim and M2M standing data update process. | Data Check | Batch Check | - Standing Data Mismatch in UIQ | Web Service call to UIQ | Yes
Meter On Correct Firmware | UIQ | This will confirm that the meter is on the correct baseline firmware. There is a daily process that will identify discrepancies in the meter firmware and will trigger an update. This will allow the program to measure the performance of baselining the meters | - Meter ID - Meter Software Version | Batch Request | - Meter Baselining Incomplete | Web Service call to UIQ | No
Meter on Approved Program | UIQ | This will confirm that the meter is on a valid approved meter program. There is a daily process that will identify discrepancies in the meter program and will highlight unapproved programs. | - Meter ID - Meter Program ID | Batch Request | - Meter Baselining Incomplete | Web Service call to UIQ | No
Meter on Baseline Program | UIQ | This will confirm that the meter is on one of the 17 baseline meter program. Non baselined meters will be baselined as a prerequisite for Logical Conversion | Data Check | Batch Request | - Meter Baselining Incomplete | Web Service call to UIQ | No | Pilot Meters that are not on the baseline program will not be upgraded to the baseline as part of the Pilot.
Meter Reporting Interval Data | UIQ | This will indicate that the meter is reporting interval data. | - Meter ID - Last Read Pointer | Batch Request | - Meter Baselining Incomplete | Web Service call to UIQ | Yes
Meter Reporting Current Interval Current Data (as at previous midnight) | UIQ | This will indicate that the meter data is current as at the previous midnight. A sharp drop in this number would indicate an application or wide scale communication issue | Data Check | Batch Request | - Communication Performance Issue | Web Service call to UIQ | Yes
Meter Reporting Interval Data Reliably | UIQ | This will measure that meter data is being routinely delivered 6 times a day for a period of 2 weeks. This will provide an indicator of readiness for logical conversion. | Data Check | Batch Request | - Communication Performance Issue | Web Service call to UIQ | No